## Summary
Summary
CSPdocMaker in plain terms. Read this sheet first; the others break each line down.
Question | Answer
What is it? | A system that makes the four documents every CSP needs — ID Card, CSP Certificate, Training Certificate and Business Continuity Plan — without anyone opening Word.
What did it replace? | Someone opening a Word file, retyping 23 details, cropping a photo, saving a PDF and writing an email. Four times, for every single CSP.
How does it start? | A new row in the Google Sheet. The system notices it within a minute. Nobody has to tell it anything.
What if something is missing? | It stops and asks the one person who can answer: the CSP for their own details, their bank manager (RM) for the bank's. It never guesses and never prints a blank.
How does the CSP reply? | They get a link that works once. It shows only what is missing, in English and Hindi. What they type goes straight back into the Google Sheet.
Is it finished? | The system works. It is not deployed — it runs on one laptop and has no backup. See the 'What is left' sheet.
How much has it been tested? | 748 automatic tests, all passing. Roughly a quarter of all the code written exists only to check the rest.
How big is it? | About 34,200 lines of code, 74 web addresses (API endpoints), 26 database tables, built between 11 September and 6 October 2026.
Has it made real documents? | Yes — 64 so far, for 8 real CSPs, including photographs.

## What was built
What was built
Everything that works today. 'Status' is what it actually does right now, not what it is meant to do.
# | Feature | What it means in plain words | Status
1 | Reads the Google Sheet by itself | Every 60 seconds it checks the CSP sheet. A new row becomes a new CSP. A changed cell updates them. Nobody presses anything. | Working
2 | Makes all four documents | Fills the bank's own Word files — the real ones, not copies — so fonts, layouts and logos stay exactly as the bank designed them. | Working
3 | Puts the photo in correctly | Every photo is passport size, 35mm by 45mm, cropped so faces are never stretched or squashed. | Working
4 | Turns them into PDFs | Converts the Word files to PDF automatically, on the server, with nobody involved. | Working
5 | Checks its own work | After making the PDF it reads it back to confirm nothing was left blank and the photo really is on the page. This caught a real fault where photos were being cut off at the eyes. | Working
6 | Emails them to the CSP | Sends the finished PDFs. If sending fails the documents are kept, so nobody is ever sent the same thing twice. | Working
7 | Refuses rather than guesses | No photo means no ID card. A missing detail stops the job and says exactly what is wanted. It never produces a half-finished document. | Working
8 | Knows who to ask | The 23 details are split by who can actually answer. 11 belong to the CSP. 8 fill themselves from the INFO sheet. Only 2 ever need a bank manager. | Working
9 | Lets the CSP fill their own gaps | A one-time link, in English and Hindi, showing only what is missing. Expires in 7 days. Their answers go straight back into the Google Sheet. | Working
10 | Three levels of access | RM sees only their own CSPs. Admin configures the system. Super Admin also controls who may sign in. Checked on the server, not just hidden on screen. | Working
11 | Secure sign-in | Passwords are scrambled and unreadable. A code is emailed on every login. Eight wrong guesses locks the account for 15 minutes. | Working
12 | Dashboards you can click | Every number opens to show the records behind it. 'Missing own details: 2' tells you which two, and what each is missing. | Working
13 | Build your own dashboards | Add a dashboard for a particular push, hide it when done, bring it back if you were wrong. No developer needed. | Working
14 | Upload new document types | Upload any Word file and the system reads its placeholders and works out what fills them. Proven with a document nobody had written any code for. | Working
15 | Six automatic assistants (agents) | Each watches one thing: is the setup complete, is any record incomplete, do the CSP's answers match, what can be issued, who needs messaging, is anything stuck. They run on their own clocks. | Working
16 | Edit the sheets from inside the system | Super Admin can view, correct, add or remove rows in the Google Sheets without leaving the application. Changes appear in the sheet immediately. | Working
17 | Record of every sign-in | Who signed in, what day, what time, from where. Super Admin only. | Working (from 6 Oct)
18 | Ready for more than one customer | Each customer's data is walled off underneath every single database query, not by remembering to add a filter. Tested with two customers at once. | Working
19 | Reads the bank's CRM safely | Pulls CSP photographs from Zoho. The access it has is read-only at Zoho's end — it physically cannot change anything there. | Working
20 | Will not send a broken link | If the link in a message would not work for the person receiving it, the message is not sent. This stopped a real email to a real CSP. | Working

## What is left
What is left
In the order the RISK sits, not the order of effort. Items 1 and 2 are not features — they are the difference between a working system and one that can be handed to somebody else.
Priority | Task | Why it matters, in plain words | Effort | Status
1 | Put the code into version control (git) | The entire project has never been saved to a code repository. It exists as loose files on one laptop with no history. One bad delete and all of it is gone. The safety settings are already in place so no passwords would be uploaded. | 30 minutes | NOT STARTED
2 | Set up backups | The only copy of all 64 documents and every CSP's data is inside one program on one laptop. That program crashed once on 5 October and came back by luck. A daily automatic copy, and restoring from it once to prove it works. | 2-3 hours | NOT STARTED
3 | Put it on a proper server | It currently runs on a laptop. If the laptop sleeps, closes or loses wifi, everything stops. It needs to live on a server that is always on. | 1 day | NOT STARTED
4 | Give it a permanent web address | Right now it only works on this one machine. Colleagues cannot reach it, and the links sent to CSPs cannot work until this is done. | Half a day (needs a domain name) | NOT STARTED
5 | Automatic testing on every change | So a change that breaks something is caught immediately rather than discovered later by a person. | 2 hours | NOT STARTED
6 | Change the Google password key | The security key for the Google Sheets has been copied around during development. It should be replaced before going live. | 30 minutes | NOT STARTED
7 | Record who changed what | Sign-ins are now recorded. Template changes, access grants and messages sent are not. With more than one person using it you would have no record of who did what. | Half a day | Part done
8 | Move the photos into the database | Photos are currently remembered as file locations on this laptop. Those locations will not exist on the server, so every photo would break on the day it moves. | 2-3 hours | NOT STARTED
9 | Finish the WhatsApp sending | WhatsApp can be set up but nothing actually sends through it yet. It says so plainly rather than failing silently. Email works. | Depends on the provider | NOT STARTED
10 | Write the messages properly | The messages to CSPs are currently signed '— Team' with no mention of EKO or SBI. A CSP receiving an unsigned message with a link is being asked to do exactly what they are trained not to. | 1 hour | NOT STARTED
11 | Test with realistic numbers | Everything so far has been tested with 8 CSPs. Nobody knows how it behaves with 800. It may be fine; it has simply never been tried. | Half a day | NOT STARTED
12 | Decide how long data is kept | There is no rule yet for how long CSP data and documents are stored, or when they are deleted. This is a policy decision before it is a technical one. | A decision, then 2 hours | NOT STARTED
13 | Add AO and RBO to the INFO sheet | These are the last two details that still need a bank manager. If the INFO sheet gained those columns they could be worked out from the district automatically, and nothing would need a human. | 1 hour once the columns exist | Planned
14 | Switch on messaging to CSPs | Everything is built and ready. It currently refuses to send because the web address is not public yet. Turning it on should be a deliberate decision, not a surprise. | Decision only | Waiting on item 4

## The six assistants
The six assistants
The system has six small automatic workers. Each watches one thing. None of them ever decides whether a document is correct — that stays exact and automatic.
Assistant | The one question it answers | How often | On?
Setup | Is this customer set up well enough to issue documents? | When asked | Yes
Data | Is any record incomplete, and who should be asked about it? | Every 15 minutes | Yes
Verification | Does what a CSP sent us agree with what we already had? | Every 30 minutes | Yes
Document | Which documents can be produced now? | Every 3 minutes | Yes
Communication | Who needs to be contacted, and did it reach them? | Every 60 minutes | Yes, but cannot send yet
Monitoring | Is anything stuck, failing, or quietly not running? | Every 10 minutes | Yes

## Timeline
Timeline
What was built and when, from the first file to today. Reconstructed from file dates and the database, because the project has no code history.
Date | What happened
11-19 Sep | First files. Sign-in built. The database designed and created.
22-23 Sep | The Google Sheets became the official source of the data. The CSP record reshaped to match the real sheet.
24-25 Sep | Documents start being stored in the database. PDF conversion added. Working out which manager owns which CSP.
28 Sep | Sign-in with emailed codes, email sending, and the first screens. Nine sets of tests written in one day.
1 Oct | Photographs pulled from the bank's CRM. The one-time link for CSPs. The passport-size photo rule enforced.
2 Oct | The biggest day: multi-customer support, three access levels, uploadable document templates, configurable dashboards, and the six assistants. 44 files.
3 Oct | Messages can actually be sent. The guard that refuses to send a broken link stops a real email.
4 Oct | Security: the technical documentation page closed off, and a limit on password guessing added where there had been none at all.
5 Oct | Photo being cut off at the eyes found and fixed. Addresses stop repeating the district twice. Names tidied to proper capitals. Dashboards became clickable. Docker crashed and was recovered.
6 Oct | The six assistants were discovered to have never actually been running, and were switched on properly. The Sheets editing screen built. Sign-in history recorded for the first time. Full documentation written.