## Summary
CSPdocMaker — changes made on 26 Oct 2026
Requests No. 146 and No. 147. Built and tested on the laptop, pushed to GitHub; the server update is still to do. Nothing that is sent, made or synced changed — see the 'Not changed' tab.
Change | Screens | Behind the scenes | Documents / checks | Total
Added | 10 | 4 | 5 | 19
Changed | 1 | 7 | 1 | 9
Removed | 1 | 0 | 0 | 1
Fixed | 0 | 0 | 1 | 1
Total | 12 | 11 | 7 | 30
Tests
Automatic checks passing (final run before the push) |  |  |  | 1297
Golden checks passing (60 cases + 2 file checks) |  |  |  | 62
Commits pushed to GitHub |  |  |  | 5
Typed in from the final test run (1297 passed, 0 failed), the golden check (62 passed = 60 cases + 2 file checks) and git log (b8c4f62, e0e1dfe, de58813, 3b90236, f484d3b). The counts above them are formulas over the Changes tab.

## Screen by screen
Screen | How to get there | Who sees it | Change | Exact change
Admin sidebar | Left menu of the admin screen | Admin, Super Admin | Added | 'Data quality' button (clipboard-tick icon) in the Setup section — after 'Agents' (Super Admin only) and before 'Messaging'. For an Admin it is the first Setup item.
Admin sidebar | Left menu of the admin screen | Admin, Super Admin | Removed | 'Data quality' from the main list under 'Emails' (it was only there on the laptop for a few hours; on the server it appears straight in Setup).
Admin top bar | Top of every admin screen | Admin, Super Admin | Added | Coloured chips to the LEFT of the moon / sun (dark mode) button: '● CSP sheet 2 min ago', '● Sign-in list …', '● Calling & Lead sheets …'. Green = on time, amber = 'late', red = 'failed' or 'stuck', grey = 'never read'. Hover a chip for details. Shown only on wide screens (laptop / desktop). If they cannot load: grey 'Sync status unavailable'. Refreshes every minute.
RM top bar | Top of every RM screen | RM | Added | The same chips, to the LEFT of the bell (notifications) icon. No failure reasons for RMs.
CSP panel | Admin → type in the top search bar → choose a CSP | Admin, Super Admin | Added | 'RBO' row, after 'AO'.
CSP panel | Admin → type in the top search bar → choose a CSP | Admin, Super Admin | Added | 'Address' row, after 'Email'.
CSP panel | Admin → type in the top search bar → choose a CSP | Admin, Super Admin | Added | Small note under each value the app filled in by itself (State, LHO, AO, RBO, Email, Address, DC, ASM, Assigned RM): 'ⓘ From INFO tab · not checked by anyone yet' (grey), '· confirmed' (green) or '· corrected' (amber). Hover = the reason, e.g. 'INFO AO block, by branch VISARWADI'. Values typed in the sheet get no note.
CSP panel | Admin → type in the top search bar → choose a CSP | Admin, Super Admin | Added | Amber line 'Where these values came from could not be read just now.' — only if that information fails to load; the panel still opens.
Data quality page (new) | Admin → Setup → Data quality | Admin, Super Admin | Added | Section 1 'Context — what the app reads': table with Sheet · Used for · Last read in full · Expected (every N min) · State (On time / Late / Stuck / Failed / Never read; red reason text when failed).
Data quality page (new) | Admin → Setup → Data quality | Admin, Super Admin | Added | Section 2 'Auto-filled values — check or correct': filter buttons 'Not checked yet' (default) · 'Corrected' · 'Confirmed' · 'All', and a search box (CSP code, name or value). Columns: CSP · Field · Value · Why this value · State · buttons. 'Show 50 more' at the bottom.
Data quality page (new) | Admin → Setup → Data quality → section 2 | Admin, Super Admin | Added | Green 'Confirm' button (only on values not checked yet): marks it right; nothing is written to the sheet.
Data quality page (new) | Admin → Setup → Data quality → section 2 | Admin, Super Admin | Added | 'Correct' button (pen icon): the value becomes a text box with 'Save to sheet' and 'Cancel' (Enter saves, Esc cancels). Saving writes it to the CSP sheet. A red message under the value if refused (changed by someone else, sheet unreachable).
Data quality page (new) | Admin → Setup → Data quality → section 2 | Admin, Super Admin | Added | Grey '🔒 Not here' instead of buttons on the RM name; hover says why (it decides who owns the CSP — change it in the sheet).
Data quality page (new) | Admin → Setup → Data quality | Admin, Super Admin | Added | Five number tiles: Filled values in use · Kept without correction (green at 75% or more, red below) · Checked by a person and kept · Corrected · Characters changed, on average.
Data quality page (new) | Admin → Setup → Data quality | Admin, Super Admin | Added | Table 'By field and source': Field · Filled from · Filled · Not checked · Confirmed · Corrected · Kept · Checked & kept · Avg. chars changed. Click a row to show only that field's corrections.
Data quality page (new) | Admin → Setup → Data quality | Admin, Super Admin | Added | Table 'Week by week': Week of · Values filled · Corrections · Avg. chars changed (shown once there is data).
Data quality page (new) | Admin → Setup → Data quality (bottom) | Admin, Super Admin | Added | Table 'Corrections': CSP · Field · The app filled · Changed to · Chars · Where, by whom · When. 'Show all' and 'Show N more' links.
Screens NOT changed today
Overview dashboard
Emails
WhatsApp messages
Messaging
Document templates
Sheets (sheet editor — looks the same; it now also records corrections)
Database
Agents
Access
Workspace rules
Knowledge Base
Build a dashboard
RM: Documents, Sheets, Database
CSP's own details form (link sent to CSPs)
Sign-in and sign-up

## Changes
Change | Area | What | Where | Who sees it | Register No. | Commit
Added | Screen | Data quality page: kept / confirmed / corrected counts, 'kept' rate (target above 75%), characters changed, week by week, list of corrections | Admin → Setup → Data quality | Admin, Super Admin | 146 | b8c4f62
Added | Screen | 'Context — what the app reads' table: each sheet, what it is used for, when last read in full, how often expected, why the newest read failed | Admin → Setup → Data quality (top) | Admin, Super Admin | 147 | de58813
Added | Screen | 'Auto-filled values — check or correct' list, with filters (Not checked / Corrected / Confirmed / All) and search | Admin → Setup → Data quality | Admin, Super Admin | 147 | de58813
Added | Screen | Confirm button: marks an auto-filled value as right (writes nothing) | Data quality → Auto-filled values | Admin, Super Admin | 147 | de58813
Added | Screen | Correct button: writes the right value to the CSP sheet (like the sheet editor); refused if the value changed since the page opened or the sheet cannot be written. Not for the RM name (it decides the owner) | Data quality → Auto-filled values | Admin, Super Admin | 147 | de58813
Added | Screen | Freshness chips (CSP sheet, Sign-in list, Calling & Lead sheets): green on time, amber late, red failed or stuck, grey never read | Top of every admin screen | Admin, Super Admin | 146 | b8c4f62
Added | Screen | The same freshness chips | Top of every RM screen | RM | 146 | b8c4f62
Added | Screen | Note under each auto-filled value, e.g. 'From INFO tab · not checked by anyone yet'; hover for the reason | Admin → search a CSP (top bar) → panel | Admin, Super Admin | 146 | b8c4f62
Added | Screen | RBO row | CSP panel (top-bar search) | Admin, Super Admin | 146 | b8c4f62
Added | Screen | Address row | CSP panel (top-bar search) | Admin, Super Admin | 146 | b8c4f62
Changed | Screen | Data quality moved from the main sidebar list into the Setup section | Admin sidebar | Admin, Super Admin | 147 | de58813
Removed | Screen | Data quality item from the main sidebar list (it is now under Setup) | Admin sidebar | Admin, Super Admin | 147 | de58813
Added | Behind the scenes | Database table field_provenance: every value the app fills in by itself, where from, why, and whether a person kept or corrected it | Database (applied by itself when the server starts) | — | 146 | b8c4f62
Added | Behind the scenes | Database table field_corrections: every change a person made to such a value — from what, to what, who, where, characters changed | Database | — | 146 | b8c4f62
Changed | Behind the scenes | CSP sheet sync also records what INFO filled in, and notices edits made in the Google Sheet — in one step after all rows are saved (about 5 ms a minute) | csp_sync_worker.py | — | 146 | b8c4f62
Changed | Behind the scenes | INFO mapping now also says WHY it chose each value (by branch, by district, by LHO and State…). The values it chooses are unchanged | info_directory.py | — | 146 | b8c4f62
Changed | Behind the scenes | Zoho fill also records what it filled and from which Lead | zoho_fill.py | — | 146 | b8c4f62
Changed | Behind the scenes | Address-tab fills, and rows copied into CSPDATA from the Calling / Lead sheets, record which cells were filled automatically | source_sheets.py | — | 146 | b8c4f62
Changed | Behind the scenes | Calling & Lead sheet job now records each run (so its chip works) | source_sheets_worker.py | — | 146 | b8c4f62
Changed | Behind the scenes | CSP's form: when submitted, notes which auto-filled values they kept or changed | csp_form_router.py | — | 146 | b8c4f62
Changed | Behind the scenes | In-app sheet editor: a change to an auto-filled value is recorded with the editor's name | sheet_router.py | — | 146 | b8c4f62
Added | Behind the scenes | Audit log entries for every Confirm and Correct on the Data quality page | Audit log | — | 147 | de58813
Added | Behind the scenes | Server endpoints: freshness, scoreboard, corrections, values, confirm, correct | quality_router.py | — | 146, 147 | b8c4f62, de58813
Added | Document / check | 60 golden cases: made-up CSP situations with their right answers (documents, AO / RBO / DC mapping, RM owner, holds, mobiles, Zoho address, what is asked, WhatsApp or email, old vs new) | backend/tests/golden/cases.json | — | 146 | b8c4f62
Added | Document / check | 101 new automatic checks: 39 for data quality, 62 golden checks (60 cases + 2 checks on the file itself, e.g. no real emails or numbers) | test_field_quality.py, test_golden_cases.py | — | 146, 147 | b8c4f62, de58813
Added | Document / check | Step: run the golden cases on the laptop before every push | DEPLOY.md | — | 146 | b8c4f62
Changed | Document / check | Made clear the golden cases run on the laptop, not on the server | DEPLOY.md | — | — | f484d3b
Added | Document / check | Decisions D15 (auto-fill record), D16 (freshness), D17 (golden cases) | AI_SPEC.md | — | 146 | b8c4f62
Added | Document / check | Requests No. 146 and No. 147 | PROJECT-REGISTER.md | — | 146, 147 | e0e1dfe, 3b90236
Fixed | Document / check | A test stand-in for INFO did not accept the new 'why' — updated (test only) | test_go_live_end_to_end.py | — | 146 | b8c4f62

## Not changed
Part of the flow | After today's changes
Documents | Which documents are made, their contents, PDF, storage — unchanged
Emails | Who is emailed, when, and the wording — unchanged (EMAILS_PAUSED still applies)
WhatsApp | Who is messaged, when, and the wording — unchanged
Verification of old CSPs | Who gets it and when — unchanged
Holds | Who is on hold and why — unchanged
Old vs new CSPs | Unchanged (checked by 8 golden cases)
AO / RBO / DC mapping | Same values chosen as before; it now also says why
What a CSP is asked | Unchanged (checked by golden cases)
If recording fails | The sync, form and sheet editor carry on; the error is logged (tested by breaking it on purpose)

## Still open
What | Details | Status
Update the server | Backup the database, then git pull and docker compose up -d --build; check the log shows upgrade a7d2c4e6f8b1 and no errors. | Waiting for you
Look at the new screens | Nobody has seen them in a browser yet (sign-in needs the emailed code). Check the chips, Setup → Data quality, the CSP panel notes. | Waiting for you
Laptop copy of the app | To show the new screens on this laptop its database needs the two new tables — back it up first (your rule). | Waiting for you
Automatic golden check before every push | A git check on the laptop that stops a push if a golden case fails. | Offered — your choice
Suggested fixes from repeated corrections | Data quality would suggest an INFO fix when people correct the same thing the same way; an Admin approves. | Offered — your choice
'Weaker match' flags | Mark values matched only by district, or from the Zoho Business Address, so they are checked first. | Offered — your choice
CLAUDE.md for the project | A short file Claude Code reads automatically, pointing to the rules and logic files. | Offered — your choice
Occasional test failure | test_an_old_csp_gets_documents_once_they_answer failed once in a slow run and passed every time after (also seen 23 Oct, No. 143). | To watch